## Yes! Get In! Dev Log
Yes! Get In!TM is a trading name of TaggUIn Ltd. COMPANY DETAILS TaggUIn Ltd is a company registered in England & Wales with company number 09158021. Its registered address is 145-157 St Johns Street, London, EC1V 4PW. © 2015 TaggUIn Ltd. All rights reserved.
[10 empty] | Today | 2015-03-07
App stage | Dev stage | Version | Comment Date | Front/ Back-end | Element | Screen | Comment by | Comment | Priority | Requested for | Days remaining | ETA | Status | What updates have been made | Updated by | Update Date | Actual time
MVP | Alpha | 1 | 2015-03-07 | Both | Functionality | Fixtures | Bhav | Please can the swipes change so, Home is left and away is right? | MUST | 2015-03-08 | 1 |  | Open
MVP | Alpha | 1 | 2015-03-07 | Backend | Content | Fixtures | Bhav | Backend setup of point allocation | MUST | 2015-03-15 | 8 |  | In progress
MVP | Alpha | 1 | 2015-03-07 | Both | Content | Rounds | Bhav | Can Last five rounds of premier league season be updated | SHOULD | 2015-03-15 | 8 |  | Open
MVP | Alpha | 1 | 2015-03-07 | Both | Content | Fixtures | Bhav | Can Fixtures for last five rounds of Fixtures | SHOULD | 2015-03-15 | 8 |  | Open
MVP | Alpha | 1 | 2015-03-07 | Backend | Feature | Live Tables | Bhav | Live Premier League table API | SHOULD | 2015-03-15 | 8 |  | Open
MVP | Alpha | 1 | 2015-03-07 | Both | Functionality | Fixtures | Bhav | When user makes no updates and taps on back button it comes up with alert window. Can this be changed so it only comes up when the user actually makes and change? | COULD | 2015-04-20 | 44 |  | Open
MVP | Alpha | 1 | 2015-03-07 | Both | Functionality | Fixtures | Bhav | Can we change method of selecting a draw from holding down for 2 secs to swiping down? | COULD | 2015-04-20 | 44 |  | Open